## Sheet1
Nº | Report Title | Publication Date | Ministry/Department | Findings | Recommendations | Page and Paragraph Reference | Ministry/Department Reponse | Response Date | Implementation Status | Actual / Expected Implementation Date | NAO Comments
1 | REPORT OF THE DIRECTOR OF AUDIT ON THE ACCOUNTS OF THE GOVERNMENT FOR THE FINANCIAL YEAR 2023-24 | 2025-03-25 | Ministry of Public Service, Administrative and Institutional Reforms | As of June 2023, the construction and completion stage for the Academic Block and Auditorium reached only 53 per cent and 43 per cent respectively. | The Accounting Officer should ensure that the New Civil Service College is completed within a reasonable timeframe. | (Pg 440, Para 24.1) | The construction works have been completed and the completion certificate was issued by the Project Consultant on 18 December 2024. | 2025-01-01 | Implemented | N/A | N/A
2 | REPORT OF THE DIRECTOR OF AUDIT ON THE ACCOUNTS OF THE GOVERNMENT FOR THE FINANCIAL YEAR 2023-24 | 2025-03-25 | Ministry of Public Service, Administrative and Institutional Reforms | The Ministry targeted the development of three sandbox project but as of September 2023, only one project was completed. | The Accounting Officer shall ensure that all constraints and challenges faced in implementing the sandbox projects and conducting BPR exercises are addressed. | (Pg 443, Para 24.3) | The Ministry of Labour was requested to submit another project in replacement of the SMS Gateway and Alert System Project. | 2025-01-01 | Not Implemented (The two Sandbox Projects, namely, the SMS Gateway and ELibrary System did not materialise in view of unsuccessful bidding exercises) | N/A | N/A
3 | REPORT OF THE DIRECTOR OF AUDIT ON THE ACCOUNTS OF THE GOVERNMENT FOR THE FINANCIAL YEAR 2023-24 | 2025-03-25 | Ministry of Public Service, Administrative and Institutional Reforms | MPSAIR did not set realistic targets for two KPIs, namely “Number of Safety Audits Conducted” and “the Number of Public Officers Trained”. | The Accounting Officer should ensure that factors such as past achievements and implementing capacity of the Ministry are considered before setting realistic targets. | (Pg 444, Para 24.3) | For future planning of Safety Audits, a realistic figure based on recent achievements of part financial years will be considered before setting targets. | 2025-01-01 | Partly Implemented | N/A | N/A
4 | REPORT OF THE DIRECTOR OF AUDIT ON THE ACCOUNTS OF THE GOVERNMENT FOR THE FINANCIAL YEAR 2023-24 | 2025-03-25 | Ministry of Public Service, Administrative and Institutional Reforms | ▪ Only three meetings of the AC were held out of the required six meetings. ▪ The AC did not submit its Status Reports for the quarters ended 31 March 2023 and 30 June 2023 to the Accounting Officer and OPSG. | The AC members and the Accounting Officer should fulfil their reporting responsibilities by complying with the provisions of the ACCharter and the PA. | (Pg 445, Para 24.4) | ▪ There was a high turnover of administrative staff within a period of five months. ▪ The Audit Committee of the financial year 2023-2024 has been reconstituted and is now fully operational. | 2025-01-01 | Implemented | N/A | N/A
5 | REPORT OF THE DIRECTOR OF AUDIT ON THE ACCOUNTS OF THE GOVERNMENT FOR THE FINANCIAL YEAR 2023-24 | 2025-03-25 | Ministry of Public Service, Administrative and Institutional Reforms | AC did not review and recommend the approval of the IA Charter as outlined in the AC Charter. | The Annual IA Plan and IA Charter should be reviewed by the AC. | (Pg 446, Para 24.5) | The Annual IA Plan and Charter could not be reviewed by the AC as it was not fully operational. | 2025-01-01 | Implemented | N/A | N/A
6 | REPORT OF THE DIRECTOR OF AUDIT ON THE ACCOUNTS OF THE GOVERNMENT FOR THE FINANCIAL YEAR 2023-24 | 2025-03-25 | Ministry of Public Service, Administrative and Institutional Reforms | Only 75 per cent of the planned audit and follow-up assignments were covered and some risky auditable areas may not have been reviewed. | The risky audit areas identified in the Annual IA Plan should be covered as far as possible. | (Pg 446, Para 24.5) | For the financial year 2022-23, 4 audit assignments have been completed. | 2025-01-01 | Partly Implemented | N/A | N/A
7 | REPORT OF THE DIRECTOR OF AUDIT ON THE ACCOUNTS OF THE GOVERNMENT FOR THE FINANCIAL YEAR 2023-24 | 2025-03-25 | Ministry of Public Service, Administrative and Institutional Reforms | Assets procured for July 2022 were recorded on the GAR online system while NFAs procured from August 2022 to June 2023 were recorded on the Application Desktop Integrator. | The Accounting Officer should arrange for effective training programmes to enable GAR users to record data in respect of NFAs on the GAR online system. | (Pg 446, Para 24.6) | All assets procured for the period August 2022 to June 2023 were recorded on the GAR online system. The Government Asset Register for the Ministry is up to date for the period ending 30 November 2024. As for assets procured in December 2024, the exercise has already been completed. | 2025-01-01 | Implemented | N/A | N/A
8 | REPORT OF THE DIRECTOR OF AUDIT ON THE ACCOUNTS OF THE GOVERNMENT FOR THE FINANCIAL YEAR 2023-24 | 2025-03-25 | Ministry of Public Service, Administrative and Institutional Reforms | As of September 2023, the Ministry did not develop a Risk Management (RM) Framework. | The Accounting Officer should establish an RM Framework and Strategy within reasonable time. | (Pg 447, Para 24.7) | In July 2024, the Accounting Officer approved the Risk Management Policy. The Risk Management Framework has been drafted with the assistance of representatives of Internal Control Unit of the Ministry of Finance. | 2025-01-01 | Implemented | N/A | N/A
9 | REPORT OF THE DIRECTOR OF AUDIT ON THE ACCOUNTS OF THE GOVERNMENT FOR THE FINANCIAL YEAR 2023-24 | 2025-03-25 | Ministry of Public Service, Administrative and Institutional Reforms | The RM Committee was set up in January 2023 but not yet operational as of September 2023. | The composition and mandate of the RM Committee, including roles, responsibilities and accountability should be clearly defined and approved by the Accounting Officer. | (Pg 447, Para 24.7) | In November 2023, the Risk Management Committee was reconstituted at this Ministry with the responsibility to establish the Risk Management Framework and strategy. The Risk Management Framework is expected to be completed by the end of the first quarter of 2025. | 2025-01-01 | Partly Implemented | N/A | N/A